## Sheet1
Pune Vidyarthi Griha’s
COLLEGE OF SCIENCE & COMMERCE
Year: 2025-26 Sem : IV |  |  |  | Class: S.Y.M.Sc.( Computer Science)
Name of Student: Varad Karve Project Title: Erp system for college(authentication and authorization module) Institute Name: PVG College of Science Company Mentor: Mrs.Rekha Joshi ,Mrs. Rajesh Darak
Weekly Report
Sr No | Date | Daily Activity | Proposed work for next week | Signature of college mentor
1 | 31/1/26 - 6/2/26 | Selected Authentication & Authorization module and finalized group members | Identify ERP user roles with mentor
2 | 7/2/26 - 13/2/26 | Collected ERP user roles from Rekha Mam | Collect database attributes for users and roles
3 | 14/2/26 - 20/2/26 | Identified required database attributes for authentication tables | Design login flow and ER diagram
4 | 21/2/26 - 27/2/26 | Created login flow and ER diagram | Prepare permission matrix (RBAC Excel sheet)
5 | 28/2/26 - 6/3/26 | Prepared role-permission Excel matrix | Improve API documentation and start UI planning
6 | 7/3/26 - 13/3/26 | Modified APIs and started UI planning | Design Admin UI interface
7 | 14/3/26 - 20/3/26 | Designed Admin UI and presented to Rekha Mam | Update APIs and database based on suggestions
8 | 21/3/26 - 27/3/26 | Updated APIs and database structure as suggested | Demonstrate APIs and create GitHub repository
9 | 28/3/26 - 3/4/26 | Demonstrated APIs to Rajesh Sir and created GitHub repository | Build complete demo npm model of our auth module and also published it to npm.
10 | 4/4/26 - 10/4/26 | Built complete demo model of Authentication module | Start integration with Admission module
11 | 11/4/26 - 17/4/26 | Integrated Admission module with Authentication module and uploaded on GitHub | Provide APIs to Admission team for testing
12 | 18/4/26 - 24/4/26 | Shared updated APIs with Admission module for testing | Will be Showing Demo to Rajesh Sir
13 | 25/4/26 - 1/5/26 | Showed demo to Rajesh Sir,and integarted Fees,SIS,admission modules using ngrok | We will try to add more integrated modules
14 | 2/5/26 - 8/5/26 | Added more modules notifications,placements,alumini modules | Trying to Integrated more modules